## Level 1 - POC Flow
Phase Order | Phase Name | Objective | Primary Owner | Approval Owner | Indicative Timeline (Weeks)
1 | POC Criteria | Define scope & success metrics | Colleague Listening Team | Product Owner | Week 1
2 | Data Sourcing | Confirm data & integrations | Integration / Tech Team | Product Owner | Week 2
3 | Survey Design | Design & approve survey | Survey / Design Team | Product Owner | Week 3
4 | Distribution | Launch survey to target audience | Colleague Listening Team | Product Owner | Week 4
5 | Dashboard & Insights | Deliver insights & dashboard | Colleague Listening Team | Product Owner + Users | Week 5–6

## Level 2 - Detailed Steps
Phase Name | Step Order | Step Description | Team Responsible | Approval Required (Y/N) | Approver | Start | End | UAT / Review Type | Output / Deliverable
POC Criteria | 1 | Define POC scope & success metrics | Colleague Listening Team | N |  | Day 1 | Day 3 |  | POC Criteria Draft
POC Criteria | 2 | Review POC criteria | Product Owner | Y | Product Owner | Day 4 | Day 7 | Review | Approved Criteria
Data Sourcing | 1 | Finalize data fields | Integration / Tech Team | N |  | Week 2 | Week 2 |  | Data Dictionary
Data Sourcing | 2 | Setup Workday → ServiceNow → SFTP | Integration / Tech Team | N |  | Week 2 | Week 2 |  | Integration Ready
Data Sourcing | 3 | UAT at data level | Colleague Listening Team | Y | Product Owner | Week 2 | Week 2 | Data UAT | UAT Sign-off
Survey Design | 1 | Compare existing survey | Survey / Design Team | N |  | Week 3 | Week 3 |  | Gap Analysis
Survey Design | 2 | Propose redesigned survey | Survey / Design Team | Y | Product Owner | Week 3 | Week 3 | Design Review | Approved Survey Design
Distribution | 1 | Define target audience & regions | Colleague Listening Team | N |  | Week 4 | Week 4 |  | Audience List
Distribution | 2 | Approve comms & distribution plan | Product Owner | Y | Product Owner | Week 4 | Week 4 | Comms Review | Distribution Approval
Dashboard & Insights | 1 | Compare existing vs new dashboard | Colleague Listening Team | N |  | Week 5 | Week 5 |  | Dashboard Comparison
Dashboard & Insights | 2 | User walkthrough & alignment | Dashboard Users | Y | Product Owner + Users | Week 5 | Week 6 | User Review | Final Dashboard

## Approval Gates
Phase | Approval Gate Name | Approver | Trigger Condition | Outcome
POC Criteria | POC Go/No-Go | Product Owner | Criteria Review Completed | Proceed / Stop
Data Sourcing | Data Readiness Approval | Product Owner | Data UAT Completed | Proceed to Survey Design
Survey Design | Survey Design Approval | Product Owner | Design Review Completed | Proceed to Distribution
Distribution | Distribution Approval | Product Owner | Comms & Audience Approved | Launch Survey
Dashboard & Insights | Final Delivery Sign-off | Product Owner + Users | User Walkthrough Completed | POC Closure