## Problem Statement & Opportunity
1. Problem Statement & Opportunity
1.1 Current Challenges
The personal fitness and wellness space in India faces a set of structural problems that limit access, quality, and outcomes for a large portion of the population.
# | Challenge
1 | Exercising without expert guidance often leads to poor form and long-term injuries
2 | Personal training is expensive and inaccessible to much of the middle-class population
3 | Lack of accountability results in high dropout rates from fitness programs
4 | Wellness services are fragmented across multiple apps and providers — no unified experience
1.2 Market Opportunity
These challenges exist against a backdrop of rapidly growing demand — creating a clear opening for a structured, intelligent wellness platform.
| Opportunity | Signal
| India's fitness industry growth | ~15% annually — one of the fastest-growing wellness markets globally
| Post-pandemic health awareness | Significantly increased consumer focus on preventive health and fitness
| Home-based fitness demand | Growing ~40% year-over-year — driven by convenience and affordability needs
| Holistic wellness interest | Rising demand for integrated solutions covering training, nutrition, and therapy

## Platform Overview
2. Platform Overview
Wellness Connect is a unified platform connecting clients with certified fitness and wellness professionals. It brings together multiple expert categories under a single experience — covering discovery, assessment, training, tracking, and outcome reporting.
2.1 The Platform
Clients connect with the following categories of certified wellness professionals:
| Professional Category | Area of Expertise
| Personal Trainers | Strength training and conditioning
| Yoga Instructors | Flexibility, mobility and mindfulness
| Ayurveda / Alternative Therapists | Traditional wellness therapies
| Nutrition Coaches | Diet planning and habit formation
2.2 Roles & Responsibilities
The platform serves five distinct roles. Each role has a defined interface, specific responsibilities, and a set of features assigned to it.
| Role | Responsibilities | Primary Interface | Features
| Client | • Register and create personal profile • Track wellness metrics and progress • Book sessions with trainers • Complete readiness check-ins | Mobile App + Web | 22 features
| Trainer | • Manage schedule and client sessions • Conduct training sessions • Track client progress • Log session notes and feedback | Mobile App + Web | 10 features
| Assessment Team | • Conduct initial health assessment after client registration • Record detailed health and lifestyle data • Recommend suitable trainers • Set up training programs • Conduct monthly audits to review progress and program effectiveness | Web Dashboard | 6 features
| Admin | • Manage onboarding of trainers and experts | Web Dashboard | 5 features
| System | • Monitor payments and platform analytics • Oversee moderation and compliance • Run scoring and risk detection engines • Execute trainer matching algorithm • Orchestrate push notifications • Generate automated wellness plans | Background Services | 7 features

## Workflow
3. Cross-Role Swimlane Workflow
Wellness Connect is a unified platform connecting clients with certified fitness and wellness professionals. It brings together multiple expert categories under a single experience — covering discovery, assessment, training, tracking, and outcome reporting.
ID | Phase (P#ID) | CLIENT (C#ID) | S.NO. | ASSESSMENT (A#ID) | SYSTEM (S#ID) | TRAINER (T#ID) | Phase Implementation | Action Plan Status | Queries / Suggestions / Remarks | Response to Queries
C1 | Phase 1 | Sign Up → Create Profile → Register → OTP Verification | 1 | — | Validate data | — | MVP
|  |  | 2 |  | Create Unique Client ID |  | MVP
|  |  | 3 |  | Store profile in database |  | MVP
C2 | Phase 1 | Profile Details + Basic Health Information | 4 | — | Validate & store profile data | — | MVP
|  |  | 5 |  | Link to Client ID |  | MVP
C3 | Phase 1 | Accept Privacy Policy, Consent Agreement and Medical Disclaimer | 6 | — | Record consent with timestamp | — | MVP
|  |  | 7 |  | Audit trail created |  | MVP
A1 | Phase 2 | — | 10 | Assessment Expert contacts client | Send appointment notification (FCM) | — | MVP |  | Not required
|  |  | 11 | Schedule assessment visit or virtual consultation
C4 | Phase 2 | Confirm assessment appointment | 12 | — | Confirm booking | — |  |  | Assessment Expert reaches client and seeks appointment confirmation, accordingly client has to confirm appointment. But, how do we track these booking records at initial stage? Manual entry may leads to miss the records and creates confusion in booking & tracking order and to keep the records in track. Vinoth: We will revisit again based on UX eperience
|  |  | 13 |  | Reserve expert slot
A2 | Phase 2 | — | 14 | Conduct detailed health assessment | Store assessment record / Link to Client ID | — | MVP |  | Future Process: Finding Health Care Expert to create structured document on enquiring health related questions to client and recording the complications in case if any exists, are required as input from client. Helps to categorize the training program to client.
|  |  | 15 | Record health and lifestyle findings in system |  |  | MVP
|  |  | 16 | Identify risk flags | Flag risk data in DB |  | MVP
A3 | Phase 2 | — | 17 | Recommend suitable trainer(s) | Trigger trainer recommendation workflow |  |  |  | How do Assessment team validates Trainer data? Vinoth: We will gather for more details on processing trainers data
|  |  | 18 |  | Run trainer matching algorithm (skill + location + availability) |  |  |  | Two Way Process: Algorithm Suggestion / Assessment Expert Selection. Initial Phase implementation goes by expert selection / suggestion to user.
C5 | Phase 3 | Select preferred trainer from shortlist | 19 | — | Notify selected trainer | Receives notification | MVP
T1 |  | — | 20 | — | — | Accept client request | MVP
T2 | Phase 3 | — | 21 |  | Generate program template | Define goals + design training program | MVP
|  |  | 22 |  | Store plan in DB |  | MVP
C6 | Phase 3 | Review and approve training goals | 23 | — | Update plan status to approved | — | MVP
C7 | Phase 4 | Book trial session | 24 | — | Reserve session slot | Confirm availability |  |  | Based on Trainers preferrence to give free trial. This is not needed for MVP. Future enhancement (if necessary based on clients feedback)
FIN1 | Phase 4 | Payment initiated | 25 | — | Payment gateway call (Razorpay) | — |  |  | Not required for MVP
FIN2 | Phase 4 | Payment confirmed | 26 | — | Settlement record created | Trainer notified of confirmation |  |  | Not required for MVP
EX1 | Phase 5 | Daily wellness tracking (weight, water, sleep, steps) | 27 | — | Store tracking data, Sync wearable data, | — | MVP |  | Vinoth will explore more details on integration options and approach.
|  | Log meals + steps | 28 |  | Store nutrition log |  | MVP
EX2 | Phase 5 | Join video / live session | 29 | — | Jitsi room created | Conduct training session | MVP |  | Zoom meeting external to our application
EX3 | Phase 6 | Complete weekly readiness check-in form | 30 | Review observations and annotate findings | Compute readiness score | — | MVP |  | Yet to prepare the Weekly readiness check-in form
|  |  | 31 |  | Run adherence engine |  | MVP
EX4 | Phase 6 | Receive injury risk alert | 32 | — | Injury risk rule fired | Receive client risk alert | MVP
|  |  | 33 |  | FCM alert dispatched | Adjust training plan | MVP
EX5 | Phase 6 | — | 34 | Escalate safety case | Set program pause flag in DB | Pause training |  |  | Not in MVP phase. Will decide based on data in MVP
|  |  | 35 | Conduct referral if required |  | Await assessment clearance
T3 | Phase 7 | Receive updated weekly plan | 36 | — | Generate weekly plan (auto-engine) | Review, Edit and approve plan before dispatch |  |  | System generation not needed
OUT1 | Phase 8 | View personal progress dashboard | 37 | Conduct monthly progress audit | Aggregate analytics across all data sources | View client monitoring dashboard | MVP
|  |  | 38 | Review program effectiveness |  |  | MVP
OUT2 | Phase 8 | Export PDF progress report | 39 | — | PDF generation engine (pdfmake.js) | Export client PDF for records | MVP

## MetaData (hidden)
ID | ID Details | Color Codes & Details: | Phase Implementation | Color Coding |  |  | Action Plan | Color Coding
FIN1 | Finance or Payment related | Less Priority
EX1 | Exercise tracking - this include food tracking, etc | Changes in Program | MVP | Gold | (255, 215, 0) | #FFD700 | Yet To Start | Light Gray | (211, 211, 211) | #D3D3D3 | ¦ **Action Plan Status** ¦ **Color Name** ¦ **RGB** ¦ **Hex** ¦
EX2 | Exercise tracking - this include food tracking, etc | Query | PHASE 1 | Light Green | (144, 238, 144) | #90EE90 | In Progress | Light Blue | (173, 216, 230) | #ADD8E6 | ¦-----------------------------------------¦----------------¦--------------------¦-------------¦
EX3 | Exercise tracking - this include food tracking, etc | Suggestions | PHASE 2 | Medium Green | (60, 179, 113) | #3CB371 | Completed | Green | (0, 128, 0) | #008000 | ¦ Yet To Start ¦ Light Gray ¦ (211, 211, 211) ¦ #D3D3D3 ¦
EX4 | Exercise tracking - this include food tracking, etc |  | PHASE 3 | Teal | (0, 128, 128) | #008080 | Cancelled | Red | (255, 0, 0) | #FF0000 | ¦ In Progress ¦ Light Blue ¦ (173, 216, 230) ¦ #ADD8E6 ¦
R1 | Risk injury |  | PHASE 4 | Light Blue | (173, 216, 230) | #ADD8E6 | Hold | Orange | (255, 165, 0) | #FFA500 | ¦ Completed ¦ Green ¦ (0, 128, 0) ¦ #008000 ¦
SAF1 | Safety steps |  | PHASE 5 | Medium Blue | (70, 130, 180) | #4682B4 | Pending | Yellow | (255, 255, 0) | #FFFF00 | ¦ Cancelled ¦ Red ¦ (255, 0, 0) ¦ #FF0000 ¦
PL1 | Planning for next week or month etc |  | PHASE 6 | Indigo | (75, 0, 130) | #4B0082 | In Discussion | Medium Purple | (147, 112, 219) | #9370DB | ¦ Hold ¦ Orange ¦ (255, 165, 0) ¦ #FFA500 ¦
AN1 | You can change this as OUT1 Output - Mainly dashboards for tracking |  | PHASE 7 | Purple | (147, 112, 219) | #9370DB | Planned For Future Implementation | Teal | (0, 128, 128) | #008080 | ¦ Pending ¦ Yellow ¦ (255, 255, 0) ¦ #FFFF00 ¦
OUT1 | Output - Mainly dashboards for tracking |  | PHASE 8 | Dark Gray | (105, 105, 105) | #696969 |  |  |  |  | ¦ In Discussion ¦ Medium Purple ¦ (147, 112, 219) ¦ #9370DB ¦
OUT2 | Output - Mainly dashboards for tracking | [9 empty] | ¦ Planned For Future Implementation ¦ Teal ¦ (0, 128, 128) ¦ #008080 ¦

## Market Research & Reference
Market Research & Reference
Competitive landscape and reference platforms — reviewed for benchmarking, feature inspiration, and market positioning.
# | Platform | Platform Type | What They Do | Key Features | What We Can Learn | Link
1 | Carbon | AI Health Coaching | Science-backed AI coaching platform focused on nutrition, training, and body composition goals. | AI coach conversations Goal-based program generation Macro & calorie tracking Progress analytics Coach oversight layer | How to design an AI coaching interaction model; balancing automation with human oversight; onboarding UX flow | https://www.joincarbon.com/
2 | InsideTracker | Biomarker & Performance | Personalised health optimisation platform using blood biomarkers, DNA, and fitness data to drive recommendations. | Blood & DNA analysis Personalised action plans Progress zone tracking Wearable integrations Longitudinal health data | How to structure health assessments and display data-driven recommendations; visualisation of health metrics over time | https://www.insidetracker.com/
3 | WellnessZ | Indian Wellness Platform | India-based wellness platform connecting users with certified trainers, yoga instructors, and nutrition experts. | Trainer & expert discovery Session booking Multiple wellness categories India-localised pricing Virtual & in-person sessions | India-specific UX conventions; service structure; trainer discovery patterns; local pricing and trust signals | https://www.wellnessz.in/
4 | Trainerize | Trainer Management SaaS | B2B platform that enables personal trainers and gyms to manage clients, deliver programs, and track progress remotely. | Training program builder Client progress tracking In-app messaging & video Habit & nutrition tracking White-label options | Trainer-side workflow design; how to structure program delivery, session logging, and client communication features | https://www.trainerize.com/
5 | Cult.fit | Omnichannel Fitness App | India's largest omnichannel fitness platform offering live & recorded classes, gym access, nutrition, and mental wellness. | Live & on-demand classes Gym network access Diet & nutrition plans Mental wellness module Cult Pass membership | How to scale across multiple wellness verticals; membership and monetisation models; India market benchmarks for engagement | https://www.cult.fit/
6 | HealthifyMe | Nutrition & Fitness App | AI + human coach-powered app for calorie tracking, fitness logging, and personalised diet and workout plans. | AI calorie & meal tracking Human nutritionist & trainer access Wearable & device sync Readiness & health scores India-specific food database | Hybrid AI + human coaching model; India food database approach; how to design nutrition tracking that works at scale | https://www.healthifyme.com/

## Interview Scripts
Wellness App – Interview Scripts
Purpose: To understand real user behavior, pain points, and expectations from trainers and clients before building the product.
TRAINER INTERVIEW SCRIPT
Opening | Set the context and build rapport
Q1 | Hey, thanks for taking time. I'm exploring how trainers currently manage clients, track progress, and deliver coaching. This is not a sales pitch — just trying to understand real challenges from your side. | Notes / Response
S1 | Current Workflow
Q2 | Can you walk me through how you currently manage your clients end-to-end? | Notes / Response
Q3 | How do you assign workout plans, track progress, and communicate with clients? | Notes / Response
Q4 | What tools / apps are you currently using? | Notes / Response
S2 | Pain Points
Q5 | What part of managing clients takes the most time or effort? | Notes / Response
Q6 | What frustrates you the most in your current process? | Notes / Response
Q7 | Have you tried any apps / platforms before? What didn't work? | Notes / Response
S3 | Data & Tracking
Q8 | Do you track steps, sleep, HRV, or nutrition? | Notes / Response
Q9 | How important is this data for your coaching? | Notes / Response
Q10 | If you had better access to this data, how would it change your coaching? | Notes / Response
S4 | Business Side
Q11 | How do you currently charge clients? | Notes / Response
Q12 | What limits you from scaling to more clients? | Notes / Response
Q13 | If something could save you time, what would you want it to handle? | Notes / Response
S5 | Opportunity Discovery
Q14 | If you could design the perfect tool for yourself, what would it do? | Notes / Response
Q15 | What is one problem you wish someone would solve for you? | Notes / Response
Close | Wrap up the interview
Q16 | This was really helpful. If I build something around this space, would you be open to trying it or giving feedback? | Notes / Response
CLIENT INTERVIEW SCRIPT
Opening | Set the context and build rapport
Q17 | Hey, I'm trying to understand how people manage their fitness and coaching today. Not selling anything — just learning what works and what doesn't. | Notes / Response
S1 | Current Behavior
Q18 | Are you currently working with a trainer or following any fitness plan? | Notes / Response
Q19 | How do you track your progress today? | Notes / Response
Q20 | What apps or tools do you use (if any)? | Notes / Response
S2 | Problems
Q21 | What's the hardest part about staying consistent with fitness? | Notes / Response
Q22 | What do you feel is missing from your current setup? | Notes / Response
Q23 | Have you ever stopped a fitness plan midway? Why? | Notes / Response
S3 | Experience
Q24 | How do you communicate with your trainer? | Notes / Response
Q25 | Do you feel your plan is personalized enough? | Notes / Response
Q26 | Do you get feedback regularly? | Notes / Response
S4 | Data Awareness
Q27 | Do you track steps, sleep, calories, or recovery? | Notes / Response
Q28 | Do you actually use this data, or just see it? | Notes / Response
Q29 | Would you want your trainer to use this data to guide you? | Notes / Response
S5 | Expectations
Q30 | What would make a fitness app or trainer experience perfect for you? | Notes / Response
Q31 | What would make you stick to a program long-term? | Notes / Response
Close | Wrap up the interview
Q32 | Thanks — this really helps. If something better existed, would you be open to trying it? | Notes / Response
What Success looks like::
| “Users struggle with consistency because of X” “Users quit mainly due to Y” “Users expect Z from a trainer/app” | Product + UX + Behavioral researcher

## CLIENT INTERVIEW SCRIPT
CLIENT INTERVIEW SCRIPT
Section | QID | Question | Type | Options | Probe (How to ask / follow-up)
Profile | Q1 | Full Name | Open
Profile | Q2 | Gender | Single | Male; Female; Non-binary; Prefer not to say
Profile | Q3 | Contact Number | Open
Profile | Q4 | Age | Open
Profile | Q5 | City : Which city do you currently live in? | Single | Chennai; Bangalore; Other
Profile | Q6 | State : Which state are you based in? | Single | Tamil Nadu; Karnataka; Maharashtra; Delhi; Telangana; Kerala; Other
Profile | Q7 | Employment Status : What is your current employment status? | Single | Office; WFH; Hybrid; Self-employed; Student; Homemaker; Other
Behavior | Q8 | Years in fitness : How many years have you been actively doing fitness or training? | Single | <6 months; 6m-1y; 1-2y; 3-5y; 5-10y; >10y
Behavior | Q9 | What is your primary fitness activity? | Single | Gym; Yoga; Running; Cycling; Swimming; Home; Sports; Dance; Other | Can you describe what a typical session looks like for you?
Behavior | Q10 | How many days per week do you typically exercise? | Single | 1-7 days; Not exercising
Behavior | Q11 | What is your primary fitness goal right now? | Single | Weight loss; Muscle gain; Flexibility; Fitness; Performance; Health; Mental; Other | Why is this goal important now?
Behavior | Q12 | Do you own or regularly use any of these? | Single | Apple; Fitbit; Garmin; Mi Band; Phone; None | How often do you use it?
Behavior | Q13 | Approximately how much do you spend on fitness per month (trainer fees, gym, apps, supplements)? | Single | <500; 500-1500; 1500-5000; 5000-10000; >10000 | Is this comfortable for you?
Behavior | Q14 | Are you currently working with a personal trainer or following a structured fitness plan? | Single | Yes; No; Sometimes | Why did you choose this?
Behavior | Q15 | How do you currently work with your trainer? | Multi | Gym; Home; Online; Pre-recorded; App; Other | What do you like/dislike about this format?
Behavior | Q16 | How long have you been working with your current trainer or plan? | Single | <1m; 1-3m; 3-6m; 6-12m; >1y | What made you continue this long?
Behavior | Q17 | How do you currently track your fitness progress? (Select all that apply) | Multi | Photos; Weight; Apps; Notes; Wearable; Trainer; Other | What do you check regularly?
Behavior | Q18 | Which fitness or wellness apps do you currently use? (Select all that apply) | Multi | Google Fit; MyFitnessPal; HealthifyMe; Cult; Strava; YouTube; Other | Which one do you use most and why?
Pain | Q19 | What makes it hardest for you to stay consistent with fitness? (Select your top 3) | Multi | Time; No accountability; Boredom; No results; Injury; Motivation; Cost; Confusion; Other | Can you share a recent example?
Pain | Q20 | What do you feel is missing from your current fitness setup? (Select all that apply) | Multi | Personalization; Feedback; Accountability; Tracking; Nutrition; Affordable; All-in-one; Other | What would improve your experience immediately?
Pain | Q21 | Have you ever stopped a fitness plan or programme midway through? | Single | Yes; No; Sometimes | When was the last time?
Pain | Q22 | What caused you to stop? (Select all that apply) | Multi | Motivation; Busy; Injury; No results; Too hard; Cost; Access; Travel; Other | What exactly happened that time?
Experience | Q23 | How do you usually communicate with your trainer? (Select all that apply) | Multi | WhatsApp; Calls; In-person; Video; App; Email; Other | Which works best for you?
Experience | Q24 | Do you feel your current fitness plan is personalised to your specific needs and goals? | Single | Yes; No; Sometimes | What makes it feel personalized or not?
Experience | Q25 | How often do you receive feedback or progress review from your trainer? | Single | Every session; Weekly; Monthly; On request; Rarely | Is this enough for you?
Experience | Q26 | What does that feedback look like? Is it useful? | Open |  | What kind of feedback do you receive? Is it useful?
Experience | Q27 | Overall, are you satisfied with your current trainer or coaching setup? | Single | Yes; No; Maybe | Why do you feel that way?
Experience | Q28 | If not satisfied, what missing | Open |  | What would make it better?
Data | Q29 | Which health metrics do you currently track? (Select all that apply) | Multi | Steps; Sleep; Weight; Calories; Water; HR; Workout; None; Other | Which metric do you care most about?
Data | Q30 | When you look at your health data (steps, sleep, etc.), what do you usually do with it? | Single | Actively use; Curious; Occasionally; Rarely; None | Can you give an example of using it?
Data | Q31 | Would you want your trainer to have access to your health tracking data (steps, sleep, recovery) to guide your training? | Single | Yes; No; Maybe | Why or why not?
Data | Q32 | What concerns, if any, would you have about sharing your health data with a trainer or app? (Select all that apply) | Multi | Privacy; Trust apps; Judgement; Unclear use; No concern; None; Other | What would make you comfortable?
Expectation | Q33 | If you could design the perfect fitness app or trainer experience for yourself, what would it look like? | Open |  | If you could design it, what would it look like?
Expectation | Q34 | What would make you stick to a fitness programme long-term? (Select your top 3) | Multi | Results; Check-ins; Flexibility; Community; Affordable; Short workouts; Nutrition; Reports; Other | Which one matters most to you?
Expectation | Q35 | How much would you be willing to pay monthly for a platform that connected you with a certified trainer, tracked your health data, and adapted your programme based on your progress? | Single | <500; 500-1000; 1000-2000; 2000-5000; >5000 | What makes it worth that price?
Closing | Q36 | If a platform like WellnessConnect existed — one that matched you with the right certified trainer, tracked your progress, and gave your trainer live visibility into your health data — how likely would you be to try it? | Single | Definitely; Probably; Not sure; Probably not; Definitely not | What would influence your decision?
Closing | Q37 | Would you be open to being contacted when we have a prototype ready to test? | Single | Yes; No
Closing | Q38 | What is the best way to reach you? (WhatsApp number or email) | Open |  | Note tone, key quotes, reactions
Closing | Q39 | Any additional observations about this respondent Tone, engagement level, strong reactions, quotes worth capturing, follow-up topics.

## Tech Team Discussion
WellnessConnect – Technical Team Discussion Guide
Initial Phase ¦ Purpose: Align the tech team on scope, architecture, and delivery priorities before build begins
01 Project Scope & MVP Boundaries
# | Discussion Topic / Question | Context & Why It Matters | Expected Answer / Decision Needed | Owner | Priority | Status / Notes
1 | What is the exact scope of the MVP? | The Workflow sheet lists Phase 1–8 steps, many marked MVP. Confirm what the absolute minimum viable product includes. | List of confirmed MVP features across all 5 roles (Client, Trainer, Assessment, Admin, System). | Product Owner + Tech Lead | 🔴 Critical
2 | Which workflow steps are deferred post-MVP? | Several steps (C7 trial session, FIN1/FIN2 payments, EX5 safety escalation, T3 weekly plan generation) are marked 'Not required for MVP'. | Documented list of deferred items with a rough timeline/phase for each. | Product Owner | 🔴 Critical
3 | How many roles need separate interfaces for MVP? | Platform Overview lists 5 roles: Client (Mobile+Web), Trainer (Mobile+Web), Assessment Team (Web), Admin (Web), System (Background). Confirm which are in MVP. | Confirmed interface matrix per role for MVP build. | Tech Lead + UX | 🔴 Critical
4 | What does 'Phase X' mean in delivery terms? | Phases 1–8 appear in the Workflow. Are these dev sprints, app user journeys, or release milestones? | Clear definition: phase = sprint / user journey / release. Shared understanding across team. | Product Owner + Tech Lead | 🟠 High
02 Tech Stack & Architecture Decisions
# | Discussion Topic / Question | Context & Why It Matters | Expected Answer / Decision Needed | Owner | Priority | Status / Notes
5 | What is the chosen tech stack (frontend / backend / DB)? | No stack is specified in the document. The team needs to lock this in before writing any code. | Confirmed: frontend framework, backend language/framework, database engine, hosting cloud. | Tech Lead | 🔴 Critical
6 | Mobile app: native or cross-platform (React Native / Flutter)? | Client and Trainer roles both need Mobile App + Web. This choice affects developer allocation and timeline. | Decision: native iOS/Android vs React Native vs Flutter. Rationale documented. | Tech Lead + Mobile Dev | 🔴 Critical
7 | What is the API architecture — REST or GraphQL? | Multiple roles interact with overlapping data (sessions, progress, plans). API design affects efficiency and scalability. | Chosen API pattern with versioning strategy (e.g., /v1/). | Backend Lead | 🔴 Critical
8 | How will the background System services be architected? | The 'System' role runs 7 background services: scoring engine, risk detection, trainer matching, FCM push, analytics, PDF gen, wellness plan orchestration. | Microservices vs monolith, queue/worker strategy (e.g., Bull, Celery), deployment plan. | Backend Lead | 🟠 High
9 | What is the database schema strategy — single DB or per-service? | Data spans users, health records, sessions, payments, notifications, audit logs — sensitive and high-volume. | DB strategy with entity relationship overview and data partitioning plan. | Backend Lead + DBA | 🟠 High
03 Key Feature Clarifications
# | Discussion Topic / Question | Context & Why It Matters | Expected Answer / Decision Needed | Owner | Priority | Status / Notes
10 | How does the Trainer Matching Algorithm work? | Workflow step A3/18 mentions an algorithm using skill + location + availability. Initial phase may use manual expert selection. | Algorithm logic, data inputs, scoring weights. Confirm: manual-first or algorithm-first for MVP. | Product Owner + Backend | 🟢 Low | Two-way noted in doc: algorithm OR expert selection
11 | What video platform is used for live sessions? | Step EX2 mentions Jitsi for room creation, but 'Zoom external to app' is noted as a remark. | Final decision: Jitsi (self-hosted), Zoom SDK (integrated), or external Zoom link. Affects UX and cost. | Tech Lead | 🔴 Critical | See EX2 remark in Workflow
12 | How are consent and medical disclaimers stored? | Step C3 requires consent with timestamp and audit trail. This is a legal/compliance requirement. | Storage format, encryption, retention policy, and who can access consent records. | Backend + Legal | 🔴 Critical
13 | What does the Weekly Readiness Check-in form contain? | Step EX3 says the form is 'yet to be prepared'. Tech team cannot build without this spec. | Finalised form fields, scoring logic, and who receives the computed readiness score. | Product Owner + Assessment Team | 🟠 High | Pending: form design
14 | What triggers the Injury Risk Alert (EX4)? | Step EX4 mentions an 'injury risk rule'. The rule logic must be defined before building the engine. | Rule conditions, data sources (check-in, tracking data), alert routing to trainer & client. | Product Owner + Backend | 🟠 High
15 | How does wearable device integration work? | Step EX1 mentions syncing wearable data. Document says 'Vinoth to explore integration options'. | Supported devices/APIs (Google Fit, Apple Health, Fitbit). Sync frequency, data mapping. | Tech Lead | 🟡 Medium | Post-MVP if not resolved
16 | How is the PDF Progress Report generated? | Step OUT2 names pdfmake.js as the generation engine. Needs template spec. | PDF template design, data sources for each section, trigger (manual / scheduled). | Frontend + Backend | 🟢 Low
04 Data, Security & Compliance
# | Discussion Topic / Question | Context & Why It Matters | Expected Answer / Decision Needed | Owner | Priority | Status / Notes
17 | How is sensitive health data secured and encrypted? | The platform stores health assessments, injury flags, lifestyle data, and medical disclaimers — all highly sensitive. | Encryption at rest and in transit, access control per role, data classification policy. | Backend Lead + Security | 🔴 Critical
18 | What is the data retention and deletion policy? | Health records, consent logs, session history — need defined retention rules for compliance (DPDP Act, India). | Retention periods per data type, soft-delete vs hard-delete approach, user data download/export capability. | Backend + Legal | 🔴 Critical | India DPDP Act 2023 compliance
19 | What authentication and authorisation method will be used? | 5 distinct roles with different permissions. OTP verification is mentioned for client signup (C1). | Auth method (JWT, OAuth2), OTP provider, role-based access control (RBAC) matrix. | Backend Lead | 🔴 Critical
20 | How is the audit trail implemented? | Step C3 requires an audit trail for consent. Other actions (risk flags, plan changes) may also need audit logs. | Which events are logged, log format, storage location, access policy. | Backend | 🟠 High
05 Integrations & Third-Party Services
# | Discussion Topic / Question | Context & Why It Matters | Expected Answer / Decision Needed | Owner | Priority | Status / Notes
21 | Which payment gateway will be used and when? | FIN1/FIN2 steps name Razorpay but are marked 'Not required for MVP'. When does payment go live? | Timeline for payment integration, Razorpay account setup, settlement flow, refund handling. | Product Owner + Backend | 🟡 Medium | Post-MVP per doc
22 | What is the FCM (push notification) setup? | Multiple steps (A1, EX4) trigger FCM notifications. Firebase project and device token management needed. | Firebase project config, notification types, token storage, fallback (SMS/email). | Backend + Mobile Dev | 🟠 High
23 | How will the assessment booking be tracked in MVP? | Step C4 has an open remark: manual entry may miss records. A lightweight booking tracker is needed. | MVP solution for booking: shared calendar, Google Sheets, or minimal in-app scheduler. | Product Owner + Tech Lead | 🟠 High | Revisit per UX — noted in doc
24 | Are there any email / SMS service integrations required? | OTP verification (C1), appointment confirmations, and trainer notifications may need email/SMS. | Chosen providers (Twilio, MSG91, SendGrid), trigger events, template designs. | Backend | 🟡 Medium
06 Delivery, DevOps & QA
# | Discussion Topic / Question | Context & Why It Matters | Expected Answer / Decision Needed | Owner | Priority | Status / Notes
25 | What is the sprint / delivery cadence? | No timeline is defined in the document. The team needs a structured delivery plan. | Sprint length, release cycle, demo cadence, go-live target date for MVP. | Product Owner + Tech Lead | 🔴 Critical
26 | What environments will be set up (dev / staging / prod)? | Proper environment isolation prevents data leakage and enables safe QA before release. | Environment strategy, CI/CD pipeline tool (GitHub Actions, Jenkins), deployment target (AWS, GCP, Azure). | DevOps / Tech Lead | 🟠 High
27 | How will the app be tested — unit, integration, E2E? | Complex multi-role flows (client → assessment → trainer) require thorough integration and E2E testing. | Testing framework choices, coverage targets, QA sign-off process before each release. | QA Lead + Tech Lead | 🟠 High
28 | What monitoring and alerting will be in place at launch? | Background services (risk engine, scoring, matching) must be observable. Downtime must be detected fast. | Monitoring stack (Datadog, Sentry, CloudWatch), alert thresholds, on-call rota. | DevOps + Backend Lead | 🟡 Medium
07 Open Items & Immediate Next Steps
Action items to complete BEFORE the first development sprint begins:
Ref | Action Item | Responsible | Target
NS-1 | Finalise the MVP feature list with role-by-role confirmation | Product Owner + Tech Lead | Week 1
NS-2 | Lock tech stack and architecture — share decision document with team | Tech Lead | Week 1
NS-3 | Confirm video platform: Jitsi vs Zoom. Spike if needed | Tech Lead | Week 1
NS-4 | Complete Weekly Readiness Check-in form design | Product Owner | Week 1
NS-5 | Define injury risk alert rules with Assessment team | Product Owner | Week 1-2
NS-6 | Set up dev / staging environments and CI/CD pipeline | DevOps | Week 2
NS-7 | Confirm wearable integration scope for MVP vs post-MVP | Tech Lead | Week 2
NS-8 | Design RBAC matrix for all 5 roles | Backend Lead | Week 2
NS-9 | Prepare data privacy and consent compliance checklist (DPDP Act) | Legal + Backend | Week 2
NS-10 | Schedule weekly tech syncs with Product Owner throughout MVP build | All | Ongoing
Document prepared to support the WellnessConnect initial Technical Team discussion ¦ Version 1.0
08 Lean Startup Team Plan — You as Product Owner ¦ Freelancers / Contractors
Strategy: You (Product Owner) anchor the team. Freelancers cover multiple roles. Hire / expand only when MVP traction demands it. Use tools & automation to reduce headcount needs.
PHASE 1 — Core MVP Team (Recommended: 3–4 Freelancers + You)
Role | Who Covers It | Responsibilities in MVP | Must-Have Skills | Useful Tools | Hire When | Headcount
Product Owner (You) | Yourself — full-time | Define & prioritise features Write user stories & acceptance criteria Coordinate all freelancers Review designs & approve deliverables Manage workflow, phases & deadlines | Product thinking Requirements writing Stakeholder management Basic tech literacy Decision-making under ambiguity | Notion / Jira Figma (review only) Slack / WhatsApp Google Meet | Already in — Day 1 | 1 (You)
Full-Stack Developer (Lead Freelancer) | 1 senior freelancer covering backend + web frontend | Build all backend APIs Database design & setup Client & Trainer web interface Auth, OTP, RBAC setup Background services (FCM, risk engine) Audit logs & consent storage | Node.js or Python (backend) React.js (web frontend) PostgreSQL or MongoDB REST API design Firebase / FCM Git & version control | Node.js / Python React.js PostgreSQL Firebase Razorpay SDK GitHub | Hire first — before any code is written | 1 Freelancer
Mobile Developer (Freelancer) | 1 freelancer covering iOS + Android | Build Client & Trainer mobile apps Integrate APIs from backend Video session flow (Jitsi/Zoom link) Push notification handling Wearable data hooks (basic) | React Native or Flutter Mobile UI/UX implementation API integration Push notifications (FCM) App store deployment basics | React Native / Flutter Expo (if React Native) Postman Firebase Xcode / Android Studio | Hire alongside Full-Stack Dev (Sprint 1) | 1 Freelancer
UI/UX Designer + Basic QA (Freelancer) | 1 freelancer covering design & testing | Design all screens for 5 roles Create component library Handoff specs to developers Manual QA of each feature Document bugs and retest | Figma (UI design) Mobile & web responsive design User flow & wireframing Basic manual testing Bug reporting | Figma Maze / Useberry (user testing) Notion (bug tracking) Loom (screen recording for bugs) | Hire before Sprint 1 design begins (Week 1–2) | 1 Freelancer
PHASE 2 — Bring In As MVP Grows (Add only when traction / complexity demands)
Role | Who Covers It | Responsibilities in MVP | Must-Have Skills | Useful Tools | Hire When | Headcount
DevOps Engineer (Part-time Freelancer) | Part-time freelancer or use managed services initially | Set up CI/CD pipeline Deploy to cloud (AWS/GCP) Manage staging & prod environments Basic monitoring & alerts | Docker / basic K8s CI/CD (GitHub Actions) Cloud deployment Monitoring tools | GitHub Actions Render / Railway (simple alt to AWS) Sentry / UptimeRobot | When you have staging + prod and need reliable deployments (~Sprint 3–4) | 1 Part-time
Assessment Team (Domain Expert) | 1 health/fitness expert (part-time consultant) | Design the health assessment form Define weekly readiness check-in fields Set injury risk flag rules Conduct monthly audits | Health & fitness expertise Assessment & screening knowledge Documentation skills | Google Forms / Typeform Notion / Google Docs | Before Assessment module is built (Phase 2 of workflow) | 1 Consultant
Legal / Compliance (One-time Consultant)
QA Specialist (Freelancer) | Dedicated QA freelancer once features stabilise | Write test cases for all flows Conduct regression testing API testing Performance & load testing Sign off each sprint release | Manual & automated testing API testing (Postman) E2E testing tools Bug tracking | Playwright / Cypress Postman Jira / Notion k6 (load testing) | When Designer+Dev QA is no longer sufficient (~Sprint 4–5) | 1 Freelancer
PHASE 3 — Post-MVP / Scale (Only after product-market fit is validated)
Role |  | Add When / Why
Data / Analytics |  | Build dashboards, analytics engine, PDF report generation (OUT1, OUT2)
2nd Backend Dev |  | Handle scale, performance, and additional microservices as user base grows
Customer Support |  | Handle trainer & client queries, onboarding issues, and complaints
Growth / Marketing |  | SEO, app store optimisation, social media, and user acquisition campaigns
TOOLS & AUTOMATION — Reduce Team Size Without Reducing Quality
Tool |  | Replaces / Reduces | How It Helps
Render / Railway |  | DevOps | Managed cloud hosting — no dedicated DevOps needed early on
Supabase / Firebase |  | Backend | Backend-as-a-service for auth, DB, and real-time — cuts backend scope significantly
GitHub Actions |  | DevOps | Free CI/CD automation — no Jenkins or dedicated pipeline engineer needed
Sentry + UptimeRobot |  | QA / DevOps | Error tracking and uptime alerts — auto-monitors without a full monitoring team
Jitsi Meet (hosted) |  | Backend | Free open-source video — no video infra to build or maintain
Razorpay |  | Backend | Plug-and-play payments — no custom payment engineering
pdfmake.js |  | Frontend | Client-side PDF generation — no separate report service needed
Notion / Linear |  | You (PO) | Lightweight project management — replaces Jira for a small team
Claude / ChatGPT |  | All roles | AI-assisted code review, content drafting, test case generation — multiplies output per person

## Project Timeline
WellnessConnect — 3-Month Project Roadmap (Weeks 1–12)
Strategy: Zero upfront investment ¦ Fundraising from Day 1 ¦ Wearable sync in MVP ¦ Go-to-Market starts at ~50% dev progress (Month 2)
|  |  |  | MONTH 1 — Foundation & Research (Weeks 1–4) |  |  |  | MONTH 2 — Build & Pitch (Weeks 5–8) |  |  |  | MONTH 3 — Launch & Scale (Weeks 9–12)
Workstream | Task / Activity | Owner | Priority | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | Status | Notes / Dependencies
▶ RESEARCH & INTERVIEWS
Research & Interviews | Define interview targets — trainers, clients, physios | Vinoth (PO) | 🔴 Critical | ● | [11 empty] | Yet To Start | Identify target profiles before outreach begins
Research & Interviews | Identify & approach trainer communities, walkathon / cyclathon groups, fitness enthusiasts | Vinoth (PO) | 🔴 Critical | ● | ● | [10 empty] | Yet To Start | Use WhatsApp groups, Instagram, local fitness events
Research & Interviews | Recruit participants — get consent to interview | Vinoth (PO) | 🔴 Critical | ● | ● | [10 empty] | Yet To Start | Use interview scripts from 'Interview Scripts' sheet
Research & Interviews | Conduct interviews via Google Meet (with recording enabled) | Vinoth (PO) | 🔴 Critical |  | ● | ● | [9 empty] | Yet To Start | Record each session. Min 5 trainers + 5 clients
Research & Interviews | Convert interview recordings to transcripts / scripts | Vinoth (PO) | 🟠 High |  |  | ● | ● | [8 empty] | Yet To Start | Use Otter.ai or Google Meet transcription
⬛ GATE 1: MVP Feature List Locked + Prototype Ready → Begin Dev
Research & Interviews | Analyse findings — extract must-have features for MVP | Vinoth (PO) | 🔴 Critical |  |  |  | ● | [8 empty] | Yet To Start | Output: final confirmed MVP feature list
Research & Interviews | Design Weekly Readiness Check-in form (fields + scoring logic) | PO + Assessment Expert | 🟠 High |  |  | ● | ● | ● | [7 empty] | Yet To Start | Needed before Assessment module is built in tech
Research & Interviews | Define Injury Risk Alert conditions & rules | PO + Assessment Expert | 🟠 High |  |  |  | ● | ● | ● | [6 empty] | Yet To Start | Input for backend risk engine build
▶ FUNDRAISING & PITCH
Fundraising & Pitch | Finalise pitch narrative & investor story (with senior advisor) | Vinoth (PO) | 🔴 Critical | ● | ● | [10 empty] | Yet To Start | Use WellnessConnect_PitchScript.docx as base
Fundraising & Pitch | Build no-cost prototype / clickable mockup for investor demo | UX Designer (Freelancer) | 🔴 Critical |  | ● | ● | ● | [8 empty] | Yet To Start | Use Figma — no dev cost. Enough to pitch the idea
Fundraising & Pitch | Identify crowdfunding platforms & research requirements | Vinoth (PO) | 🟠 High |  | ● | ● | [9 empty] | Yet To Start | Options: Ketto, Milaap, Wishberry, Seedrs (equity)
Fundraising & Pitch | Prepare investor one-pager & pitch deck | Vinoth (PO) | 🔴 Critical |  |  | ● | ● | [8 empty] | Yet To Start | Problem, solution, market size, team, ask
Fundraising & Pitch | Begin outreach to early investors / advisors / angels | Vinoth (PO) | 🔴 Critical |  |  |  | ● | ● | ● | [6 empty] | Yet To Start | Lead with prototype + interview data as proof
Fundraising & Pitch | Pitch to senior advisor — request formal involvement | Vinoth (PO) | 🔴 Critical | ● | [11 empty] | Yet To Start | Meeting already planned — use speaking script
Fundraising & Pitch | Finalise revenue model (subscription tiers, trainer commission) | Vinoth (PO) | 🟠 High |  |  | ● | ● | ● | [7 empty] | Yet To Start | Needed before investor conversations go deep
▶ TECH DEVELOPMENT
Tech Development | Align & confirm MVP feature list (with interview data + team) | Vinoth (PO) + Tech Lead | 🔴 Critical | ● | ● | [10 empty] | Yet To Start | No dev starts until this is locked
Tech Development | Finalise tech stack, architecture & system design | Tech Lead (Freelancer) | 🔴 Critical |  | ● | [10 empty] | Yet To Start | Refer Tech Team Discussion sheet — Section 02
Tech Development | Set up dev environment, GitHub repo, CI/CD pipeline | Full-Stack Dev (Freelancer) | 🔴 Critical |  | ● | [10 empty] | Yet To Start | Use Render / Railway to avoid DevOps cost
Tech Development | Build: User auth, OTP, registration, role setup (Client / Trainer / Assessment) | Full-Stack Dev | 🔴 Critical |  |  | ● | ● | [8 empty] | Yet To Start | Phase 1 workflow: C1, C2, C3
Tech Development | Build: Health assessment flow, client profile, consent & audit trail | Full-Stack Dev | 🔴 Critical |  |  | ● | ● | [8 empty] | Yet To Start | Phase 2 workflow: A1, A2, C4
Tech Development | Build: Trainer matching, trainer profile, session booking | Full-Stack Dev + Mobile Dev | 🔴 Critical |  |  |  | ● | ● | [7 empty] | Yet To Start | Phase 2–3: A3, C5, T1, T2
Tech Development | Build: Mobile app — Client & Trainer interfaces (iOS + Android) | Mobile Dev (Freelancer) | 🔴 Critical |  |  | ● | ● | ● | ● | [6 empty] | Yet To Start | React Native or Flutter — parallel to backend
Tech Development | Integrate wearable device sync (Google Fit / Apple Health) | Full-Stack + Mobile Dev | 🔴 Critical |  |  |  |  | ● | ● | [6 empty] | Yet To Start | Core MVP feature — needed for tracking data
Tech Development | Build: Daily tracking — meals, steps, sleep, workouts (EX1) | Full-Stack + Mobile Dev | 🟠 High |  |  |  |  | ● | ● | [6 empty] | Yet To Start | Phase 5 workflow: EX1
Tech Development | Build: Video session integration — Jitsi or Zoom link (EX2) | Full-Stack Dev | 🟠 High | [5 empty] | ● | ● | [5 empty] | Yet To Start | Decision needed: Jitsi self-hosted vs Zoom link
Tech Development | Build: Weekly readiness check-in form + scoring engine (EX3) | Full-Stack Dev | 🟠 High | [5 empty] | ● | ● | [5 empty] | Yet To Start | Depends on form design from Research stream
Tech Development | Build: Injury risk alert engine + FCM push notifications (EX4) | Full-Stack Dev | 🟠 High | [6 empty] | ● | ● |  |  |  |  | Yet To Start | Depends on risk rules from Research stream
⬛ GATE 2: ~50% Dev Complete → Go-to-Market & Investor Pitch Begins
Tech Development | Build: Progress dashboard + PDF report generation (OUT1, OUT2) | Full-Stack + Mobile Dev | 🟠 High | [7 empty] | ● | ● |  |  |  | Yet To Start | pdfmake.js for PDF — Phase 8
Tech Development | Internal QA & bug fixing — all flows end-to-end | UX Designer + Full-Stack Dev | 🔴 Critical | [8 empty] | ● | ● |  |  | Yet To Start | Test all 5 roles across web + mobile
Tech Development | Beta testing with real trainers & clients (closed group) | Vinoth (PO) + All Devs | 🔴 Critical | [9 empty] | ● | ● |  | Yet To Start | Use interview recruits as beta testers
Tech Development | Bug fixes, performance tuning & app store submission | All Devs | 🔴 Critical | [10 empty] | ● | ● | Yet To Start | iOS App Store + Google Play submission
⬛ GATE 3: MVP Launch + Crowdfunding Campaign Live
▶ GO-TO-MARKET
Go-to-Market | Define GTM strategy — target segments, channels, messaging | Vinoth (PO) | 🟠 High |  |  |  | ● | ● | [7 empty] | Yet To Start | Starts when dev is ~50% complete (~Week 6-7)
Go-to-Market | Corporate outreach — offer wellness sessions to companies | Vinoth (PO) | 🟠 High | [5 empty] | ● | ● | ● |  |  |  |  | Yet To Start | B2B angle — HR teams are a good entry point
Go-to-Market | Hospital & physio clinic partnerships — co-branding / referrals | Vinoth (PO) | 🟠 High | [5 empty] | ● | ● | ● |  |  |  |  | Yet To Start | Ask for banner placement, referral agreements
Go-to-Market | Influencer outreach — fitness YouTubers, Instagram coaches | Vinoth (PO) | 🟠 High | [6 empty] | ● | ● | ● |  |  |  | Yet To Start | Affiliate / referral link model — no upfront cost
Go-to-Market | Digital marketing setup — social media pages, content plan | Vinoth (PO) | 🟡 Medium | [6 empty] | ● | ● | ● | ● |  |  | Yet To Start | Instagram, LinkedIn, YouTube shorts for awareness
Go-to-Market | Trainer recruitment campaign — onboard first 10–20 trainers | Vinoth (PO) | 🔴 Critical | [7 empty] | ● | ● | ● |  |  | Yet To Start | Platform needs trainers before client launch
Go-to-Market | Soft launch — invite-only to first 50 clients | Vinoth (PO) + All | 🔴 Critical | [10 empty] | ● |  | Yet To Start | Controlled launch — gather real usage data
Go-to-Market | Public launch + crowdfunding campaign goes live | Vinoth (PO) | 🔴 Critical | [11 empty] | ● | Yet To Start | Launch + raise together for maximum momentum
▶ OPERATIONS & COORDINATION
Operations & Coordination | Weekly team sync — PO + all freelancers (30 min) | Vinoth (PO) | 🔴 Critical | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | Yet To Start | Every week throughout the project — non-negotiable
Operations & Coordination | Maintain & update this project timeline weekly | Vinoth (PO) | 🟠 High | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | Yet To Start | Update status column every Friday
Operations & Coordination | Hire & onboard Full-Stack Developer (freelancer) | Vinoth (PO) | 🔴 Critical | ● | [11 empty] | Yet To Start | Must be in place before Week 2
Operations & Coordination | Hire & onboard Mobile Developer (freelancer) | Vinoth (PO) | 🔴 Critical | ● | ● | [10 empty] | Yet To Start | In place by Week 2 to start mobile build
Operations & Coordination | Hire & onboard UI/UX Designer (freelancer) | Vinoth (PO) | 🔴 Critical | ● | [11 empty] | Yet To Start | Needed for prototype + mobile/web design
Operations & Coordination | Engage Health / Assessment Domain Expert (consultant) | Vinoth (PO) | 🟠 High |  | ● | ● | [9 empty] | Yet To Start | Needed for assessment form + risk rule design
Operations & Coordination | Legal consultant — consent, DPDP Act, T&C review | Vinoth (PO) | 🟡 Medium |  |  |  | ● | ● | [7 empty] | Yet To Start | One-time engagement before MVP launch
Operations & Coordination | Set up project tools — Notion/Linear, Slack, GitHub, Figma | Vinoth (PO) | 🔴 Critical | ● | [11 empty] | Yet To Start | Free tools — zero cost setup
LEGEND
● Research & Interviews |  |  |  | ● Fundraising & Pitch |  |  |  | ● Tech Development |  |  |  | ● Go-to-Market |  |  |  | ● Operations & Coordination
Yet To Start |  |  | In Progress |  |  | Completed |  |  | On Hold |  |  | Blocked

## Intelligence Engine Specs
WellnessConnect — Intelligence Engine Specifications
Four rule-based engines · Zero external API dependency · Pure backend logic
5.1 Client Readiness Score Engine (#44) — Composite score 0–100 representing client readiness for next session
Input Factor | Weight | Data Source | Source Type | Refresh Frequency | Notes
Mobility Score | 25% | Assessment form, check-in responses | Manual | Weekly | Client self-reported + trainer assessment
Pain Stability | 25% | Weekly check-in, injury log | Manual | Weekly | Flags if pain is increasing across check-ins
Sleep & Recovery | 20% | Wearable sync, manual tracking | Wearable + Manual | Daily / Weekly | Wearable preferred; fallback to manual input
Session Attendance | 20% | Booking records, session history | System (auto) | Real-time | Auto-logged on session completion
Risk Flags (inverse) | 10% | Injury risk detection engine output | System (auto) | Per check-in | Pulls from Engine 5.3; lowers score on red/yellow
5.2 Program Adherence Score Engine (#45) — Measures how closely a client follows their assigned program (0–100)
Input Factor | Weight | Data Source | Source Type | Refresh Frequency | Notes
Sessions Attended | 40% | Session history, booking records | System (auto) | Real-time | Primary adherence signal; auto-captured
Habit Completion | 30% | Daily manual wellness tracking | Manual | Daily | Client logs habits; reminder prompts improve rate
Check-in Completion | 20% | Weekly readiness check-in form | Manual | Weekly | Missing check-ins reduce adherence score
Trainer Feedback Score | 10% | Session notes, trainer ratings | Trainer (manual) | Per session | Trainer scores effort/engagement post-session
5.3 Injury Risk Detection Logic (#46) — Detects elevated injury risk from negative signal combinations
Signal Pattern | Threshold / Condition | Source Type | Refresh Frequency | Alert Level | Action Triggered
Pain level increasing | 3+ consecutive check-ins rising | Manual | Weekly | 🟡 YELLOW | Trainer notified automatically
Mobility score declining | >15% drop over 2 weeks | Manual + System | Weekly | 🟡 YELLOW | Trainer notified automatically
Fatigue score high | 7+ days above fatigue threshold | Wearable + Manual | Daily | 🟡 YELLOW | Rest day recommended to client
Pain + Mobility↓ + Fatigue↑ | All three signals simultaneously | Manual + Wearable | Per check-in | 🔴 RED | Assessment Team escalation triggered
5.4 Plan Adjustment Rule Engine (#47) — Auto-recommends program modifications based on readiness + adherence signals
Condition | Signal / Trigger | Source Type | Refresh Frequency | Priority | Recommended Action
High progress | Readiness > 80 AND Adherence > 80 | System (auto) | Weekly | 🟢 Growth | Advance program — increase intensity/volume
Stagnant progress | No improvement for 3+ weeks | System (auto) | Weekly | 🟡 Review | Modify approach — introduce variety or method change
Injury risk elevated | Risk score > 70 | Engine 5.3 | Per check-in | 🔴 Urgent | Regress program — reduce intensity and volume
Low engagement | Adherence < 40 for 2 consecutive weeks | Engine 5.2 | Weekly | 🟠 Attention | Simplify program — reduce complexity, add check-in
Source Type Legend: | Manual = Client self-reported | Wearable = Auto-synced device data | System (auto) = Platform-generated | Trainer = Coach-entered | Engine X.X = Output from another engine

## Notification Strategy
Notification Strategy
WellnessConnect ¦ FCM Push · Email · In-App ¦ MVP Phase — triggers, recipients, frequency & opt-out
A Onboarding & Registration
ID | Trigger Event | Recipient(s) | Message Template | Channel | Timing | Frequency Cap | MVP Priority | Opt-Out Allowed? | Notes
N01 | Client completes OTP verification | Client | Welcome to WellnessConnect! Your account is ready. [CTA: Complete your profile] | FCM Push + Email | Immediate | Once only | 🔴 Critical | No | Triggers after C1 workflow step
N02 | Assessment appointment scheduled | Client | Your health assessment is booked for [Date/Time]. Our expert will contact you shortly. | FCM Push | Immediate | Once per booking | 🔴 Critical | No | Triggers after A1 — Step 10
N03 | Client profile setup incomplete after 24h | Client | You're almost there! Complete your profile to get matched with a trainer. | FCM Push | 24h after signup | Max 2 reminders | 🟠 High | Yes | Nudge — re-engagement
N04 | Trainer accepted client request | Client | Great news! [Trainer Name] has accepted your request. Your program starts soon. | FCM Push + In-App | Immediate | Once only | 🔴 Critical | No | Triggers after T1 — Step 20
N05 | New trainer profile approved by Admin | Trainer | Your WellnessConnect profile is now live! Clients can discover you. | Email | Immediate | Once only | 🔴 Critical | No | Admin-triggered after trainer onboarding
B Session Management
ID | Trigger Event | Recipient(s) | Message Template | Channel | Timing | Frequency Cap | MVP Priority | Opt-Out Allowed? | Notes
N06 | Session booked by client | Trainer | New session booked: [Client Name] on [Date] at [Time]. Confirm your availability. | FCM Push + In-App | Immediate | Once per booking | 🔴 Critical | No | Triggers after C7/booking step
N07 | Session reminder — 24h before | Client + Trainer | Reminder: Your session with [Name] is tomorrow at [Time]. See you there! | FCM Push | 24h before session | Once per session | 🔴 Critical | Yes | Both roles receive separately
N08 | Session reminder — 1h before | Client + Trainer | Your session starts in 1 hour. Tap to join your video session. | FCM Push | 1h before session | Once per session | 🟠 High | Yes | Include video link if applicable
N09 | Trainer marks session as completed | Client | Session complete! Log how you're feeling today to help your trainer plan next week. | In-App | Immediate | Once per session | 🔴 Critical | No | Prompts post-session check-in
N10 | Session marked as no-show (client) | Trainer | [Client Name] did not attend today's session. You may reschedule or log a note. | FCM Push + In-App | Immediate | Once per event | 🔴 Critical | No | Feeds session_status = no_show
N11 | Session cancelled | Client + Trainer | Your session on [Date] has been cancelled. [Reason if provided] | FCM Push + In-App | Immediate | Once per event | 🔴 Critical | No | Both parties notified. cancelled_by logged.
C Health Tracking & Check-ins
ID | Trigger Event | Recipient(s) | Message Template | Channel | Timing | Frequency Cap | MVP Priority | Opt-Out Allowed? | Notes
N12 | Weekly readiness check-in due | Client | Time for your weekly check-in! How are you feeling this week? [CTA: Complete now] | FCM Push | Weekly — Monday 9am | Max 2 reminders/week | 🔴 Critical | No | Feeds EX3 workflow — readiness score engine
N13 | Daily wellness log not submitted | Client | Don't forget to log today's meals, steps & sleep. Keeps your score accurate! | FCM Push | Daily 8pm (if no log) | Max 1/day | 🟠 High | Yes | Soft nudge — reduce if user consistently logs
N14 | Readiness score computed | Trainer | [Client Name]'s weekly readiness score is ready: [Score]/100. Review their check-in. | In-App | After score computed | Once per week | 🔴 Critical | No | Trainer dashboard update — feeds intelligence engine
N15 | Wearable sync failed / disconnected | Client | Your wearable device hasn't synced in 2 days. Reconnect to keep your data accurate. | FCM Push | After 48h no sync | Max 1 per 3 days | 🟡 Medium | Yes | Post-MVP if wearable integration deferred
D Risk & Safety Alerts
ID | Trigger Event | Recipient(s) | Message Template | Channel | Timing | Frequency Cap | MVP Priority | Opt-Out Allowed? | Notes
N16 | Injury risk — YELLOW flag triggered | Trainer + Client | ⚠️ Heads up: [Client Name]'s risk signals are elevated. Review their check-in before the next session. | FCM Push + In-App | Immediate (per check-in) | Once per flag event | 🔴 Critical | No | Feeds EX4 — Engine 5.3 YELLOW threshold
N17 | Injury risk — RED flag triggered | Trainer + Assessment Team | 🔴 Urgent: [Client Name] has multiple injury risk signals. Assessment Team review required. | FCM Push + In-App + Email | Immediate | Once per event | 🔴 Critical | No | Engine 5.3 RED threshold — escalation required
N18 | Program paused by Assessment Team | Client + Trainer | Your training program has been temporarily paused pending a safety review. We'll be in touch shortly. | FCM Push + Email | Immediate | Once per event | 🔴 Critical | No | EX5 workflow — requires Admin action
E Program & Progress Updates
ID | Trigger Event | Recipient(s) | Message Template | Channel | Timing | Frequency Cap | MVP Priority | Opt-Out Allowed? | Notes
N19 | Training program approved by client | Trainer | [Client Name] has approved the training goals. You can now begin scheduling sessions. | FCM Push + In-App | Immediate | Once only | 🔴 Critical | No | Triggers after C6 — Step 23
N20 | Weekly plan updated by trainer | Client | Your trainer has updated your plan for next week. Check what's new! | FCM Push + In-App | Immediate | Once per update | 🟠 High | Yes | Triggers after T3 plan update
N21 | Monthly progress report ready | Client + Trainer | Your monthly wellness report is ready. See your progress, scores & next steps. | FCM Push + Email | Monthly (auto) | Once per month | 🟠 High | Yes | OUT1/OUT2 — PDF report generation trigger
N22 | Plan adjustment recommended by engine | Trainer | The system has suggested a plan adjustment for [Client Name]. Review and approve before dispatch. | In-App | After engine run | Once per suggestion | 🟠 High | No | Engine 5.4 — trainer must approve before client sees
N23 | Assessment monthly audit due | Assessment Team | Monthly audit reminder: [Client Name]'s program is due for review this week. | In-App + Email | Monthly | Once per audit cycle | 🟠 High | No | Assessment Team dashboard — keeps compliance on track
F Global Frequency Rules (apply across all notification types)
Rule | Details
Daily cap | Max 3 push notifications per user per day (all types combined). Research shows 2–5/week is the opt-out threshold.
Quiet hours | No push notifications between 10pm – 7am IST. Schedule pre-dawn reminders for 7am delivery.
Opt-out handling | All non-critical notifications (N03, N07, N08, N13, N15, N20, N21) must have opt-out toggle in user settings.
Critical overrides | Safety alerts (N16, N17, N18) and booking confirmations (N06, N09) bypass frequency cap — always delivered.
Batching | If multiple low-priority notifications queue for same user on same day, batch into a single digest push at 6pm.
Platform rules | Follow Apple APNS and Google FCM guidelines. Request notification permission at a meaningful moment (post-first booking, not signup).

## Trainer Recruitment
Trainer Recruitment & Onboarding
WellnessConnect ¦ Supply-Side Strategy ¦ Target: 15–30 certified trainers before client launch
1 Target Trainer Profiles (who we need)
Category | Description | Certifications Expected | Volume Target (MVP) | Where to Find Them | Priority | Notes
Personal Trainers | Strength, conditioning, functional fitness coaches for 1:1 sessions | ACE, NASM, ISSA, or equivalent Indian cert (FTII, NSCA) | 8–10 trainers | Gyms (Chennai, Bangalore, Hyderabad), Instagram fitness coaches, TrainerConnect India | 🔴 Critical | Core category — most client demand will be here
Yoga Instructors | Flexibility, mobility, pranayama, mindfulness coaching | RYT-200 or RYT-500 (Yoga Alliance), Iyengar, Sivananda cert | 4–6 instructors | Yoga studios, NamasteYoga India community, local ashrams, Instagram | 🔴 Critical | Strong India-specific demand post-pandemic
Nutrition Coaches | Diet planning, macro coaching, habit formation — not clinical dietitians | INFS, Precision Nutrition, ACSM Certified Nutrition Coach | 3–5 coaches | LinkedIn, Indian nutrition forums, HealthifyMe trainer alumni | 🟠 High | Avoid clinical dietitians — out of scope, increases liability
Ayurveda / Alternative Therapists | Traditional wellness, Panchakarma, herbal guidance | BAMS degree or diploma from accredited Ayurveda institute | 2–3 therapists | Kerala Ayurveda clinics, AYUSH-registered practitioners, wellness centres | 🟡 Medium | Differentiator vs competitors — small batch for MVP
2 Recruitment Channels
Channel | Approach | Target Trainer Type | Estimated Reach | Cost | Timeline | Status
WhatsApp fitness groups | Join trainer communities, share brief pitch + landing page or Google Form. Personal outreach to interested trainers. | Personal Trainers, Yoga | 30–50 contacts per group | Zero cost | Week 1–2 | Yet To Start
Instagram DM outreach | Identify trainers with 1K–50K followers who post client content. DM with personalised message. | All categories | 20–30 per week | Zero cost | Week 1–3 | Yet To Start
Gym partnerships | Approach 5–10 gyms in target city (Chennai first). Offer trainers a free listing + tools in exchange for trial. | Personal Trainers | 5–10 per gym | Zero cost (commission later) | Week 2–4 | Yet To Start
LinkedIn outreach | Search "personal trainer Chennai", "yoga instructor Bangalore". Connect + send note. | Nutrition Coaches, Trainers | Targeted — 10–15 quality leads | Zero cost | Week 2–3 | Yet To Start
Referral program | Every onboarded trainer refers 2 others. Incentive: priority client matching or featured profile. | All categories | Scales with each signup | Zero cost | Week 4 onwards | Yet To Start
Fitness events / walkathons | Attend local fitness events — already in Project Timeline. Recruit trainers in person. | Personal Trainers, Yoga | 5–15 per event | Entry fee only | Week 2–4 | Yet To Start
3 Trainer Onboarding Workflow (step-by-step)
Step ID | Action | Responsible | System Involvement | Verification Required | MVP? | Notes
TR-01 | Trainer expresses interest (via form, DM, or referral) |  | Google Form / landing page captures name, category, city, cert details | No | Yes | Simple intake form — no platform needed at this stage
TR-02 | Initial screening call — verify background, intent, availability |  | None — manual call / Google Meet | Yes — verbal check | Yes | 15-min call. Check: professional experience, client base, communication quality
TR-03 | Certification document collection |  | Google Drive folder per trainer | Yes — document review | Yes | Collect: cert scan, ID proof, selfie with cert. Store securely.
TR-04 | Admin creates trainer account on platform | Admin (Web Dashboard) | Admin feature: create trainer profile, assign Trainer ID | System-generated ID | Yes | Admin role — this is one of the 5 Admin features. Needs to be built.
TR-05 | Trainer completes profile on platform | Trainer (Mobile/Web) | Profile fields: bio, specialisation, city, availability, photo | Profile completeness check | Yes | Minimum completeness threshold before going live (e.g. 80%)
TR-06 | Platform agreement and consent sign-off | Trainer | Digital consent form — timestamp recorded (similar to C3 client consent) | Audit trail created | Yes | Covers: platform T&Cs, code of conduct, data consent, commission terms (future)
TR-07 | Trainer profile reviewed and approved by Admin | Admin | Admin toggles trainer status from "Pending" to "Active" | Yes — Admin sign-off | Yes | Trainer not discoverable by clients until approved. Sends N05 notification.
TR-08 | Trainer profile goes live — visible to Assessment Team for matching | System | Trainer indexed in matching pool (skill + location + availability) | No | Yes | Feeds A3 trainer recommendation workflow — Step 17/18
TR-09 | Orientation briefing — platform walkthrough |  | Optional: recorded video guide or live call | No | Yes (lightweight) | 30-min walkthrough: how to manage sessions, log notes, use dashboard
4 Trainer Status States (data model reference)
Status | Description | Set By | Discoverable by Clients? | Can Accept Bookings? | Notification Triggered | Notes
Pending | Trainer account created but profile/docs not yet reviewed | Admin (TR-04) | No | No | — | Default on account creation
Active | Fully verified, live on platform, available for matching | Admin (TR-07) | Yes | Yes | N05 — profile live | Normal operating state
Suspended | Temporarily paused — under review or violation concern | Admin (manual) | No | No (existing sessions continue) | N18-type alert to active clients | Admin can reinstate or remove
Inactive | Trainer-initiated pause (vacation, unavailable period) | Trainer (self-service) | No | No | Clients notified if mid-program | Future state — not MVP
Removed | Permanently offboarded | Admin | No | No | Active clients reassigned by Admin | Future state — documented for schema
5 MVP Recruitment Target Tracker
Category | Target Count | Recruited | Screened | Onboarded (Active) | Notes | —
Personal Trainers | 10 | — | — | — | Priority city: Chennai first, then Bangalore
Yoga Instructors | 5 | — | — | — | At least 2 with virtual session capability
Nutrition Coaches | 4 | — | — | — | Must be non-clinical — habit + diet coaching only
Ayurveda / Alt. Therapists | 2 | — | — | — | Nice-to-have for MVP — don't delay launch for this
TOTAL TARGET | 21 | 0 | 0 | 0 | Update as recruitment progresses