## Glint_4269_Architecture
Task ID | Task Name | Description | Team Required | Owner | Start Date | End Date | Timeline (Duration) | Dependencies | Remarks / Risks
T1 | Field Requirement Collection | CL team provides required survey and reporting fields based on business needs. | CL Team, HR | HR Tech Lead |  |  | 5 Days | Stakeholder availability | Delay in approvals may impact schedule
T2 | Architecture Review | Review current data architecture and integration landscape. | Tech Team, GTIS, CDO | Solution Architect |  |  | 4 Days | Completion of field requirements | Misalignment may require redesign
T3 | Source Data Extraction | Extract required data from Workday and ServiceNow. | Tech Team, GTIS | Integration Lead |  |  | 7 Days | System access approval | Incomplete access may block progress
T4 | Homogenized File Creation in Prism | Consolidate multi-source data into a standardized file in Prism. | Tech Team, Data Team | Data Engineer Lead |  |  | 6 Days | Source data availability | Data format mismatch risk
T5 | Master File Generation | Generate final master file from homogenized data. | Tech Team | Platform Engineer |  |  | 3 Days | Completion of Prism processing | Processing failure risk
T6 | SFTP Configuration | Configure and validate Vivagnant SFTP connectivity. | GTIS, Security, Tech | GTIS Lead |  |  | 4 Days | Firewall and security approvals | Connection failure risk
T7 | File Transfer to SFTP | Push master file to Vivagnant SFTP environment. | Tech Team, GTIS | Integration Lead |  |  | 2 Days | SFTP setup completed | Transfer failure risk
T8 | Target Field Mapping | Map source fields to Glint survey and reporting fields. | Data Team, CDO, Tech | Data Architect |  |  | 5 Days | Approved data model | Mapping errors may affect surveys
T9 | Target Documentation | Prepare target mapping and service documentation. | Tech Team, Governance | Program Manager |  |  | 3 Days | Field mapping approval | Documentation gaps
T10 | Connectivity Testing (NG-Cart) | Test SFTP and data ingestion using sample files. | QA, Tech Team | Test Manager |  |  | 4 Days | Test environment readiness | Test failures
T11 | End-to-End Validation | Validate full data flow from source to Glint platform. | HR, Tech, Governance | Program Manager |  |  | 5 Days | Successful connectivity testing | Late defect discovery
T12 | Final Sign-off | Obtain business, technical, and governance approvals. | HR, CDO, Leadership | Program Sponsor |  |  | 3 Days | Successful validation | Approval delays