## Slide 1
HR Experience Project
Glint Implementation
Group-Based Sampling Approach for 59 Journeys
Survey Design · Configuration · Deployment

## Slide 2
Overview
To avoid survey fatigue, employees are pre-assigned to one of 5 groups. Each group receives a unique subset of journeys via Glint display logic.
Group 1
Journeys 1–11
e.g. Tech
1
Group 2
Journeys 12–24
e.g. Sales
2
Group 3
Journeys 25–36
e.g. HR
3
Group 4
Journeys 37–48
e.g. Finance
4
Group 5
Journeys 49–59
e.g. Ops
5

## Slide 3
Implementation Roadmap
Phase 1
Planning
Journey groups · Cohort criteria · Group mapping
Phase 2
Data Prep
Reference data · Pre-assignment · Validation
Phase 3
Glint Config
Survey setup · Group column · Display logic
Phase 4
Testing
Group paths · Edge cases · UAT
Phase 5
Deployment
Data load · Activation · Launch monitoring
Phase 6
Post-Launch
Data quality · Support · Analysis
Sequential phases ensure reliable survey rollout across all 5 employee groups

## Slide 4
Phase 1 — Planning & Phase 2 — Data Preparation
Phase 1 — Planning
1.1
Define Journey Groups
Group 1–5 mapped to Journeys 1–11 through 49–59
1.2
Define Cohort Criteria
Dept type, seniority, tenure, role category, previous responses
1.3
Document Group Assignments
Tech → G1, Sales → G2, HR → G3, Finance → G4, Ops → G5
Phase 2 — Data Preparation
2.1
Create Reference Data Source
Employee ID, Name, Dept, Group (1–5), Activity Score
2.2
Pre-assign All Employees
Every employee must have a valid group value assigned
2.3
Validate Data Quality
Check missing IDs, duplicates, null/invalid group values

## Slide 5
Phase 3 — Glint Configuration
3.1
Create Glint Survey
Set up the survey in Glint with all 59 journeys loaded and ready
3.2
Add Group Column
Custom attribute: Survey_Group (Number 1–5), linked to employee data feed
3.3
Set Up Display Logic
G1→J1–11 · G2→J12–24 · G3→J25–36 · G4→J37–48 · G5→J49–59
3.4
Configure Question Order
Define journey ordering per group — fixed sequence or adaptive

## Slide 6
Phase 4 — Testing
4.1
Group Path Testing
Create test accounts per group · Verify correct journeys appear · Check order and no duplicates
4.2
Edge Case Testing
No group assignment · Employee switching groups · Empty/partial responses
4.3
Performance Testing
Survey load time · Completion rate tracking · Data captured correctly per group
4.4
UAT with Sample Users
2–3 real employees per group · Record time-to-complete · Capture feedback and log issues

## Slide 7
Phase 5 — Deployment & Phase 6 — Post-Launch
Phase 5 — Deployment
5.1
Final Data Load
All group assignments loaded to Glint production
5.2
Deploy Survey
Activate and confirm live for all groups
5.3
Monitor Launch
First 24–48 hrs: response rates, display logic, correct journeys
Phase 6 — Post-Launch
6.1
Monitor Data Quality
Daily: completion rates, group distribution, answer quality
6.2
Support & Troubleshooting
Wrong journeys, display errors, data sync issues
6.3
Analysis & Reporting
Cross-group comparison, cohort patterns, learnings for next iteration

## Slide 8
Key Considerations
No Native Randomization
Group-based display logic workaround pre-assigns cohorts — same effect, no Glint limitation.
Data Source Integration
Employee data feed (AD/HR system) must be synced with Glint before launch.
Display Logic Limits
Verify Glint supports 5 conditional branches; reduce to 3–4 groups if needed.
Employee Communication
Inform employees surveys are personalised — different people see different questions by design.
Response Rate Impact
11–13 journeys (vs. 59) expected to improve completion rates and data quality.
Data Analysis
Group comparisons require statistical adjustments as cohorts answer different questions.
Maintenance
Update group assignments when org structure changes. Plan periodic data refresh cycles.
Fallback Plan
If display logic fails, activate fallback: manual group routing or skip patterns.

## Slide 9
Glint Field Planning — 100 Field Limit
5
Employee Identity
5
Demographics & Location
7
Job Attributes
2
Survey Grouping
19
Total Defined
81
Remaining Budget
Key Fields Defined:
Survey_Group (Number 1–5) — single field driving all display logic · Cohort_Label — human-readable label (e.g. Tech–Senior)
Using a single Survey_Group field (vs. 5 boolean fields) saves 4 fields from the 100-field budget — the recommended approach.

## Slide 10
Next Steps
1
Finalise cohort criteria and group assignments
2
Build and validate employee reference data source
3
Configure Glint survey with display logic
4
Run testing across all 5 groups
5
Set go-live date and communicate to employees