## Sheet1
# | Area | Challenge Description | Impact | Root Cause (Observed) | Request / Recommendation
1 | Connection Stability Post ServiceNow Upgrade | After each ServiceNow upgrade (e.g., San Diego, Yokohama), the Qualtrics connection breaks. Re-establishing the integration requires starting from scratch (account creation, connection setup, workflow rebuild). | High manual effort and downtime. Delays in survey triggering post-upgrade. | Unknown; likely due to lack of coordinated investigation between ServiceNow, Qualtrics, and Engineering teams. | Investigate persistent connection failures. Enable connection reusability. Design integration to be upgrade-resilient.
2 | Credential Refresh Issues (Every 3–4 Months) | Authentication tokens or credentials fail every 3–4 months. This breaks the workflow and prevents task creation in ServiceNow. | Surveys are not triggered, leading to data loss and broken colleague feedback loops. | Token expiration or credential mismanagement. No auto-refresh in place. | Enable automatic credential refresh. Add monitoring/alerts for upcoming expiration. Improve failure transparency.
3 | API Rate Limitation (Bulk Case Closures) | If HR closes >75 cases per minute, Qualtrics drops excess cases due to API rate limits. Workflows for these cases fail. | Incomplete feedback collection. Missed survey triggers without any alert. | Hard API limit in Qualtrics; no queuing or fallback logic. | Support batch processing or queueing. Notify when threshold is crossed. Consider increasing the limit or allowing controlled exceptions.
4 | Limited Workflow History Retention | Workflow run history is only available for the past 30 days in Qualtrics. No visibility beyond that window. | Inability to audit, troubleshoot, or analyze historical failures. Loss of traceability for older issues. | Default Qualtrics retention period not configurable. | Allow history retention beyond 30 days (e.g., 6 months). Provide export or API access to archive logs externally.
5 | Siloed Operations | No coordinated investigation or ownership across ServiceNow, Engineering, and Qualtrics teams. Issues go unresolved or reoccur. | Slower resolution, repeated issues, unclear accountability. | Lack of shared documentation, process, and ownership. | Set up cross-functional ownership. Document known issues. Define joint SOP for upgrades and credential renewal.
6 | Lack of Monitoring and Alerting | No alert system for failed workflows or authentication errors in Qualtrics. Failures often go unnoticed. | Hidden data loss and delayed issue detection. | No built-in alerting from Qualtrics side. | Implement monitoring dashboard or email alerts for integration health and failed tasks.